## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | Admin Registration | As an admin, I want to open admin registration page and save the entered admin details. | Task#1 | Create a Login JSP page to accept UserId and Password and allow to login and provide with registration link. | High | Vinne | 28/3/19 | 28/3/19 | 5 |  | Done
|  |  |  | Task#2 | Create a jsp pageand redirect to Admin Registration Page | High | Vinne | 28/3/19 | 29/3/19 | 11 |  | Done
|  |  |  | Task#3 | Admin Registration Field Validation | Medium | Vinne | 29/3/19 | 29/3/19 | 1 |  | Done
|  |  |  | Task#4 | Submit the data and store it in the database | High | Vinne | 29/3/19 | 29/3/19 | 3
|  |  |  | Task#5 | Create User Entity class, User DAO and User Service class to insert the admin data and controller and verify on backend. | High | Vinne | 29/3/19 | 30/3/19 | 3.5
|  |  |  | Task#6 | Successful login | High | Vinne | 29/3/19 | 30/3/19 | 0.5
| #2 | Admin Home | As an admin, I want to land on Admin Home page which will display all the policies from the database | Task#7 | Create a jsp page for Admin Home and successfully land on it after validating credentials. | High | Prince | 31/03/19 | 31/03/19 | 3 |  | Done
|  |  |  | Task#8 | Fetch all the policies from the database by creating Policy class, Policy DAO, Policy Service and controller | High | Prince | 31/03/19 | 2019-01-04 | 11 |  | Done
|  |  |  | Task#9 | Create a 'Add Policy' and redirect to Add Policy Page and submit the details in the database. | High | Prince | 2019-02-04 | 2019-02-04 | 10 |  | Done
|  |  |  | Task#10 | View the policy details by fetching it from the database using the policy id and displaying it on a new page | High | Prince | 2019-03-04 | 2019-04-04 | 13 |  | Done
|  |  |  | Task#11 | Edit policy details by updating it in the database using the policy id and displaying it on a new page |  | Prince | 2019-05-04 | 2019-06-04 | 9
|  |  |  | Task#12 | Integrate the code and verify its working. | High | Prince | 2019-06-04 | 2019-06-04 | 2 |  | Done
|  | User Registration | As an user, I want to open user registration page and save the entered user details. | Task#13 | Create a registeration JSP page to accept the data from user as per the field of user table. | High | Ayushi | 2019-06-04 | 2019-06-04 | 2 |  | Done | We have taken userId as the primary key and assigned userType as 'U' for user.
|  |  |  | Task#14 | Create User Entity class, User DAO and User Service class to insert the user data and controller and verify on backend. | High | Ayushi | 2019-06-04 | 2019-08-04 | 15 |  | Done
|  |  |  | Task#15 | Integrate the code and verify its working . | High | Ayushi | 2019-08-04 | 2019-09-04 | 15 |  | Done
| #3 | User Home | As an user, I want to land on User Home page which will display all the policies from the database | Task#12 | Create a jsp page for User Home and successfully land on it after validating credentials. | High | Daksh | 2019-10-04 | 2019-10-04 | 2 |  | Done
|  |  |  | Task#13 | Fetch all the policies from the database. | High | Daksh | 2019-10-04 | 2019-10-04 | 3 |  | Done
|  |  |  | Task#14 | View the policy details by fetching it from the database using the policy id and displaying it on a new page | Medium | Daksh | 2019-10-04 | 2019-11-04 | 5 |  | Done
|  | Policy Payment | As an user, I want to buy the policy and make payment via different payment methods and update the status from pending to paid | Task#15 | By clicking on the 'Payment' one should be redirected to payment page which has options on it. | High | Tapas | 2019-11-04 | 2019-11-04 | 2 |  | Done
|  |  |  | Task#16 | Create a jsp page with payment options | Medium | Tapas | 2019-11-04 | 2019-11-04 | 2 |  | Done
|  |  |  | Task#17 | After redirecting and selecting a valid payment method, Payment Details Page would be loaded | High | Tapas | 2019-11-04 | 2019-11-04 | 3
|  |  |  | Task#18 | Create a UserPolicy entity, UserPolicy DAO, UserPolicy Service and controller | High | Tapas | 2019-12-04 | 13/4/2019 | 10
|  |  |  | Task#19 | Create a BankDetails entity, BankDetails DAO, BankDetails Service and controller | High | Prince | 13/4/2019 | 14/4/2019 | 10
|  |  |  | Task#20 | Enter the valid Card number and CVV number and update in the database | Medium | Prince | 14/4/2019 | 14/4/2019 | 3
|  |  |  | Task#21 | After successful payment receipt is generated and payment status changed to paid | High | Prince | 14/4/2019 | 14/4/2019 | 2
|  |  |  | Task#22 | Integrate the code and verify its working. | High | Daksh | 15/4/2019 | 15/4/2019 | 6